## Read me
Requirement → implementation → tests → status.
Sources: project brief (MVP), HR decision record, pilot readiness, UI overhauls.

## Traceability
ID | Requirement | Implemented in | Verified by | Status
MVP-1 | Synthetic data: 50 agents, 4 queues, skills, availability, 2 weeks of 30-min volumes | data_gen.py, basepack.py | test_staffing, test_data_system | Done
MVP-2 | Transparent seasonal forecast with uncertainty band | staffing.forecast | test_staffing | Done
MVP-3 | Erlang C staffing chain per queue | staffing.py | test_staffing | Done
MVP-4 | Manual heuristic baseline and recovery baseline | baseline.py | test_planning, test_acceptance | Done
MVP-5 | CP-SAT global optimiser with hard rules, ≤ 60 s | optimizer.py | test_constraints, test_planning | Done
MVP-6 | Disruption injection | workflow.report_absence, evidence.py | test_recovery, test_workflow | Done
MVP-7 | Coverage risk engine (Critical / At risk / Healthy) | risk.py, priority.py | test_recovery | Done
MVP-8 | Recovery engine: generate → filter → simulate → rank → approve → re-solve; escalate residual | recovery.py, workflow.py | test_recovery, test_workflows_e2e | Done
MVP-9 | Team-lead decision with mandatory reason; logging | services.decide_incident, comms.audit | test_services, test_app | Done
MVP-10 | Leave request Green/Amber/Red with alternatives | requests.py, workflow.submit_leave | test_workflow | Done
MVP-11 | Exception-first control tower (Ops) | views/ops.py | test_app, test_ui_overhaul | Done
MVP-12 | Evidence: ablation and H1–H5 | evidence.py | test_acceptance | Done (simulated; H1–H5 pass)
H5 | Zero hard-rule violations (independent checker) | constraints.py, workflow.transaction | test_constraints, test_isolation | Pass
HR-01 | Separation with safeguards, timing 00:00 IST, idempotent deactivation | hr.py, services.run_separations | test_hr_record, test_hr_gaps | Done
HR-02 | Opening balances, verification, ledger | hr.py | test_hr_record, test_hr_feed | Done
HR-03 | Configurable leave-review triggers | hr.evaluate_triggers | test_hr_record | Done
HR-04 | 48 h attendance lock and HR-reviewed corrections | hr.is_locked, services.review_attendance_correction | test_hr_record | Done
HR-05 | Confidential absence flags (off pending validation) | hr.absence_events | test_hr_record | Done (disabled by policy)
HR-06 | Overtime approval (off by default) | hr.evaluate_overtime | test_hr_record | Done (off)
HR-07 | Restricted HR cases | services._case_gate | test_hr_record, test_matrix | Done
HR-08 | Retention deferred, register shown | hr.RETENTION_REGISTER | test_hr_record | Done
SEC-1 | Password storage, policy, lockout, forced change, idle sign-out | security.py, auth.py | test_security | Done
SEC-2 | Single sign-on (OIDC) | auth.sso_sign_in, views/login.py | test_security | Built; needs identity provider
SEC-3 | Server-side permissions for every action | services.py | test_matrix | Done (53 actions × 6 roles = 318 combinations)
OPS-1 | PostgreSQL with backups, drill, health, alerts | db.py, pgbackup.py, jobs.py, health.py | test_postgres, test_ops | Done; hosting needed
OPS-2 | Email copies and test email | mailer.py | test_email_relay | Done locally; relay needed
DATA-1 | Imports from Excel/CSV/paste/text with validation and approvals | convert.py, dataflow.py | test_data_system, test_importer | Done
DATA-2 | HR system leave-balance feed | hr.read_balance_file, dropfolder.py | test_hr_feed | Done
UI-1 | Six role screens, areas, breadcrumbs, light/dark themes | views/, navigation.py, ui_kit.py | test_navigation, test_app, test_ui_overhaul | Done
UI-2 | Employee profile photos with initials fallback | photos.py, views/hr.py | test_photos, test_ui_overhaul | Done
UI-3 | Coverage matrix, calendars, enterprise charts | ui_kit.py, ui_common.py | test_ui_overhaul | Done
A11Y | Keyboard, names, contrast, responsive; screen-reader session | ui_kit.py | test_app (contrast), evidence/accessibility | Automated checks pass; live screen-reader session pending